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PROCESS- Music at Tynwald Day and Associated Events
Including associated/required forms for approval
Elements
	Garden Party
	President’s Dinner
	Tynwald Day


	Band (rota)

	Fanfare
	Military band & 
· appointment of band (tri-service rota)
· appointment of fanfare team
· detailed instructions including Manx repertoire


	
	Strings
	Trumpeters

	
	Band
	Hymns & Cleveland solo
· choice of hymns & Cleveland soloist repertoire
· Chapel organist & Cleveland accompanist
· St John’s choir
· Local trumpeters – appointment & rehearsal
· Local trumpeters – musical arrangements

	
	
	Manx organ music at the end of the service

	
	
	


Band at Beat Retreat?
Contacts
Garden Party – Engagement team contacts all suppliers
President’s Dinner – Engagement team contacts all suppliers
Beat Retreat – Government House 

Jonathan King is the initial contact for:
· St John’s Choir
· The Cleveland Medal Winner
· Organist 
· Trumpeters

Process
Use the month by month BUT search for key words Music and Band not just the filter.
Key Dates
January - TCAC meeting confirm musical proposals across all events. Chance to highlight any issues.
April – Manx Music Festival (usually the last Saturday of April) – to invite Cleveland winner as soloist	
Hymn choice and Order 
1) Once the Cleveland winner is known, JK contacts and ask them to choose what they want to sing as their solo
2) Once the solo is known, JK confirms hymns to go around it, avoiding duplication (the song “Isle of Mona” is sometimes done as a hymn, and sometimes as a solo)
3) JK invites the President to approve the solo and hymns as a whole.
In terms of the hymn choices, I tend to go with the same as last year unless I have had representations during the year that somebody feels the need for a change. Some Presidents like to put in ideas of their own, others less so.
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